## Slide 1: Hawai‘i State Systemic Improvement Plan (SSIP)
Early Intervention PARTNER MEETING
November 13, 2024

## Slide 2: AGENDA
Purpose of Meeting
SSIP Overview /Workgroup Updates
Feedback & Discussion
Next Steps
Notes: Here is our agenda for today.

## Slide 3: Purpose of Today’s Meeting
Review State Systemic Improvement Plan (SSIP) – Indicator 11 of the Annual Performance Report (APR)
Review Data for the SSIP, FFY 2023 (July 1, 2023 – June 30, 2024)
Establish Targets for Indicator 11
Identify Strategies for Improvement
Notes: The purpose of today’s meeting is to:
Review the SSIP which is Indicator 11 of the APR
Review the data for SSIP FFY 2023 (July 1, 2023 to June 30, 2024). This report will be submitted to the Office of Special Education Programs (OSEP) on Feb. 1, 2025.
The OSEP is the federal agency that oversees the implementation of IDEA, Part C.
Identify what is needed to improve early intervention system of services for each of the 4 areas within the SSIP. These 4 areas will be introduced later in today’s presentation.

## Slide 4: SSIP Purpose
Increases capacity of Early Intervention (EI) Programs to implement, scale up, and sustain evidence-based practices (EBPs)
Improves outcomes for children with special needs and their families
Notes: The State Systematic Improvement Plan is a comprehensive, ambitious, yet achievable multi-year plan for improving results for infants an toddlers with special needs. The SSIP will be part of the State Performance Plan (SPP) and Annual Performance Report (APR) which are viewed as critical components of the Office of Special Education Programs – OSEP’s Results Driven Accountability (RDA) system. (Refer to RDA Core Principles Handout)
OSEP’s directive is that it is of utmost importance to improve the results for infants and toddler with special needs by improving early intervention services. All of us, EI Partners that include parents, EI providers, HEICC members, and community partners are critical participants in improving results for children with special needs and together we are tasked with developing, implementing, evaluating, and revising the SSIP.
“Round 1 of the SSIP” had three phases over six years (FFY 2013 – FFY 2018) with a one year extension: Phase 1 was data analysis; Phase II was developing the plan: and Phase III ( last three years) was implementation and evaluation. The SSIP will continue and we are in Round 2 of the SSIP (FFY 2020 – FFY 2025).
Hawaii selected to focus on social-emotional development knowing that a child’s ability to connect with others and form relationships has a positive impact in all areas of their life. Also, anyone who touches the life of a child has the potential to promote healthy social-emotional development and well-being for the child.

## Slide 5: EARLY INTERVENTION OUTCOMES
Child Outcomes:
Children have positive social and emotional skills
Children learn and use knowledge and skills
Children take action to meet their needs
Notes: There are national outcomes established by OSEP that all States must report on with the notion that “Families who benefit from services are better prepared to help their children.”
These are 3 outcomes for children and 3 outcomes for families.
Children have positive social and emotional skills – such as developing trusting relationships with the people who take care of them, getting along well with family, making friends, knows how to act with different people like family members or strangers, understand and express feelings, attachment/separation/autonomy; following rules related to groups and interacting with others-
Children learn and use knowledge and skills – learn and do new things such as, thinking; reasoning; using symbols and language; understanding physical and social worlds; remembering; solving problems.
3. Children take action to meet their needs – can get what they need such as taking care of basic needs like hunger, warmth, security; getting from place to place; using tools, contributing to own health and safety.
A good way to remember the 3 child outcomes is: R.I.I.= Relationships, Intelligence, & Independence.
These Early Intervention Outcomes are for all children under age 5 in Part B and Part C. These outcomes would be endorsed by ANY parent, whether or not their child had any special needs. Parents want their kids to love them and interact with them in positive ways; Parents want them to have friends. Of course, parents want them to develop and learn. And parents want them to take action to meet their needs, even though they might disagree with their family, friends, neighbors, etc. about what actions they should take at what age. The Outcomes established by OSEP are for ALL children and Early Intervention should strive to achieve the Outcomes for all of the children receiving services.

## Slide 6: EARLY INTERVENTION CHILD OUTCOMES
Summary Statement 1 = children that entered below age expectations and substantially increased their rate of growth by the time they exited the program.
Summary Statement 2 = children functioning within age expectation by the time they exited the program, includes children that entered below age expectations and at age expectation.
Notes: Indicator 3 is a results indicator. Indicator 3 measures the three child outcomes established by OSEP. Each outcomes measures improvement in two categories:
Summary Statement 1: Children who entered early intervention below age expectations who substantially increased their rate of growth by the time they exited.
  NOTE: substantially increased = moving at least one rating above the entry rating.
Summary Statement 2: Children who were functioning within age expectations by the time they exited, regardless of where they were functioning when they entered early intervention.

## Slide 7: State Identified Measurable Result (SIMR)
  Hawai‘i’s eligible infants and toddlers with special needs served by demonstration sites will make greater than expected growth in social-emotional (SE) skills (including social relationships) by the time they exit early intervention.
Chart: Demonstration Site SIMR
| Windward ECSP | PCDC Waipahu | Kailua ES | Imua - Maui County | Demo Site Total
FFY 2020 | 0.0909 | 0.3729 | 0.4565 | 0.5924 | 0.459
FFY 2021 | 0.4286 | 0.1818 | 0.2286 | 0.3846 | 0.2807
FFY 2022 | 0.3333 | 0.6078 | 0 | 0.4535 | 0.4847
FFY 2023 | 0.5641 | 0.5909 | 0 | 0.5909 | 0.414
Program | ‘20 | ‘21 | ‘22 | ‘23
Demo Sites | 45.9% | 28.1% | 48.17% | 41.40%
Imua Maui County | 59.2% | 38.9% | 45.35% | 59.09%
Kailua ES | 45.7% | 22.9% | NA | NA
PCDC Waipahu | 37.3% | 18.2% | 60.78% | 59.09%
Windward ECSP | 9.1% | 42.9% | 33.33% | 56.41%
NOTE: Kailua ES pulled out of being a Demo Site eff. 07.01.2022
47.25%
Notes:   The State Identified Measurable Result, known as the SiMR is the long-term outcome. Hawaii’s identified SiMR is that eligible infants and toddlers with special needs served by demonstration sites will make greater than expected growth in social-emotional skills (including positive social relationships) by the time they exit early intervention (Summary Statement 1).
  For FFY 2022, one of the three programs met the target, two of the three demonstrated progress and one program had slippage and did not meet the target. For that one program, the Program Manager position was vacant for almost six months which may have impacted the providers in the program. The providers in that program was also being pulled to support other sister programs. Overall, the demo sites collectively meet the target.

## Slide 8: Target Setting
OSEP set guidelines for states on setting targets—they must:
  Be “measurable and rigorous”
  FFY 2025 must show improvement from baseline
  Get stakeholder input
  Use state data to set targets
Results Indicators - State determines targets
Indicator 11: SSIP
Child Outcomes Summary Statement 1: Positive Social Emotional Skills (including positive relationships) for Demo Sites
  Hawai‘i Part C Early Intervention will annually review and adjust targets accordingly based on data, evaluation of the impact of initiatives implemented, and stakeholder discussions.
Baseline Data: | 
FFY 2020 | 45.95%
Target | FFY Year
FFY Year | 
2020 | 45.95%
2021 | 45.95%
2022 | 45.95%
2023 | 47.25%
2024 | 47.50%
2025 | 48.00%
Notes: The Office of Special Education Programs (OSEP) put out a new State Performance Plan (SPP)/Annual Performance Report (APR) package for FFY 2020 – FFY 2025. Therefore, States were required to establish targets for results indicators for each year which we did last year.
EIS proposed to change the baseline data from FFY 2013 to FFY 2020 for the following reasons:
  February 2015: The baseline was changed to FFY 2013 data when Hawaii changed its eligibility definition to no longer serve the environmentally at-risk population. As a result, the number of children and families served in Part C declined significantly and the needs of the population of children and families served changed. However, it takes approximately three years after a change to see how it impacts the system. Therefore, baseline should have changed to FFY 2016 data. Also, there were additional initiatives that have occurred that may further impact the system.
  FFY 2020 outcome data were based on a smaller number of exited children, which impacted outcome results.
  Previous targets were based on data prior to COVID-19.
  It will take time to recover from the impacts of COVID-19.
  Further data analysis needed: will work with national TA to conduct data analysis on evaluation plan and comparing Demonstration Site Data with other Program data
COVID-19 Impact:
During the COVID-19 pandemic, when Hawai‘i implemented the use of complete Interim IFSPs due to the inability to administer the BDI-2 to determine eligibility, COS ratings were completed at the time of the Interim IFSP. This was done to ensure COS ratings were obtained prior to the start of services. Children who exited with an Interim IFSP were not included in the COS ratings above. Only children who exited with a completed Initial IFSP and received services for at least six months were included in the COS ratings calculations.
Rationale: In order to propose a change to our baseline data, we would have to have strong justifications beyond just not meeting targets. Because we changed our baseline in FFY2020, we do not propose to change it at this time. Programs are still dealing with the aftermath of Covid, and now with the Wildfires, we do not yet know what the impact will be for our families and programs. This is an area that can be revisited each year.

## Slide 9: SSIP Intermediate Outcomes
EI Providers will implement EBPs to support SE development with fidelity.
EI providers will implement the Child Outcome Summary (COS) process with fidelity.

## Slide 10: State SSIP Broad Improvement Strategies
Professional Development and Technical Assistance: Enhance the statewide system of professional development (PD) to ensure implementation of EBPs.
Fiscal: Increase the capacity of EI programs to provide services and supports to address SE development.
Monitoring and Accountability: Enhance the COS process to ensure data are accurate and reliable and ensure program effectiveness to support EBPs to improve children’s SE development.
Notes: Based on the confirmed root causes, Stakeholders brainstormed improvement strategies to address the root causes. The Leadership Team compiled the improvement strategies and for Phase I, developed broad improvement strategies in the following areas noted in slide.

## Slide 11
Notes: This is a visual to show what each workgroup did and will be focusing on related to infrastructure development and implementation practices.
The PD & TA and the Monitoring & Accountability workgroup both developed guidelines, handouts, training and providing on-going TA to support implementation of practices.
The Fiscal Staffing workgroup funded trainings identified by the PD & TA workgroup, will be establishing the team structure needed, including access to behavioral support specialists to support programs in implementing EBPs.
The Fiscal Telepractice workgroup identified and funded necessary equipment, developed guidelines, handouts and training to support implementation of TP.
The PD & TA workgroup developed the process regarding implementing the EBPs with fidelity; the Staffing workgroup will assess the implementation of the Recruitment and Retention strategies; the TP will assess how programs effectively use TP for service delivery; and the M & A workgroup developed the process of implementing the COS process with fidelity.
Each workgroup will share what they’ve accomplished in Round 1 of the SSIP, what changes they propose based on the data collected and/or realignment needed to achieve the SiMR.

## Slide 12: State SSIP Implementation Workgroups
Professional Development and Technical Assistance
Co-Lead: Jennifer Endo & Wendy Li
Fiscal
Staffing Co-Leads: Chris Pelayo and Brianne Sarmiento
3. Monitoring and Accountability
Co-Leads: Kathy Kubo and Kelli Yoshimura
Notes: There are three State SSIP Implementation Workgroups that are comprised of various stakeholders (EI Programs, HEICC members, Community Partners, and families).

## Slide 13: Professional Development and Technical Assistance
  Short-term Outcomes:
  EI providers will understand the SE competencies needed to support SE development of infants and toddlers.
  EI providers will implement EBPs in delivering EI services.
Notes: The professional development and technical assistance workgroup addressed these outcomes…
Early intervention providers will understand the Social Emotional competencies needed to support Social Emotional development of infants and toddlers.
Early intervention providers will implement Evidence Based Practices in delivering Early Intervention services.

## Slide 14: Professional Development and Technical Assistance
  Current Activities to Support the Outcomes:
  Re-examine competencies related to SE development
  Develop and implement training plan that address SE competencies and EBPs
Notes: The activities to support outcomes are to:
Re-examine Social Emotional competencies so it is in alignment with national initiatives and evidence-based practices. This includes, modifying and developing a training plan that address Social Emotional competencies within the framework of the primary service provider (PSP) approach to teaming and coaching model practices with fidelity currently being implemented.
Notes: Social Emotional national initiatives
Early Interventionist Early Childhood Special Educators (EI-ECSE) Standards & (Early Childhood Personnel Center-ECPC)
NCPMI/Pyramids
Infant & Early Childhood Mental Health (IECMH)

## Slide 15: Pulse Check: Key Accomplishments to Infrastructure for implementation of EBP in FFY 2023
Continued FST observations and support to program managers
Social Emotional Competencies
    AIM-HI: Infant Mental Health training
    AIM-HI: Reflective Supervision & Consultation training
    IECMH: Part C cross-state technical assistance
Notes: Our key accomplishments this past year include:
Continued FST observations and support to program managers by assigned TAs. Program managers are also able to identify strengths and challenges in their team and come up with next steps to address and implement change. TAs continue to support the program manager in improving the quality of team discussions as they are challenged by vacancies and staff turnover.
SE competencies:
In April 2024, AIMHI 10-month virtual learning services based on Infant Mental health Competencies with EI supervisors, program managers, TA, direct service, and care coordinators was completed. Participants developed skills and knowledge in working with diverse families as well as deepened their infant and early childhood mental health expertise.
  In August 2024, AIMHI year-long Reflective supervision/consultation training series including follow-up small group discussions around implementing reflective supervision was also completed. This series focused on developing skills and experience necessary to provide high-quality competency based reflective supervision to staff.
  Hawaii also continues to participate in cross-state cohort technical assistance focused on Infant & Early Childhood Mental Health (IECMH) policies and practices and early intervention (Part C). (TA began in October 2022.)

## Slide 16: Infant Mental Health & Reflective Supervision/Consultation Data
Infant Mental Health Foundations: n= 172
  # Completed all sessions including reflections – 77 (45%)
  # Completed partial (1-9 session) – 95 (56%)
Reflective Supervision/Consultation: n=36
  # Completed all sessions including reflections – 33 (92%)
  # Completed partial (1-9 session) – 3 (8%)
Notes: Here is some preliminary data for the Infant Mental Health Foundations training:
Of the 172 staff that completed the foundations training, 77 (45%) completed all 10 sessions. 95 (56%) completed between 1 and 9 sessions. Some reasons may include staff who were on extended leave, staff who resigned or were hired mid-way through the training series. However, additional analysis of the data is needed.
For reflective supervision/consultation, 33 (92%) completed all sessions, and 3 (8%) completed partial sessions.

## Slide 17: Confidence Rating in working with infant & early childhood mental health
Chart: 
| Prior to my first session, I would rate my CONFIDENCE working in infant & early childhood mental health as: | After my last session, I would rate my CONFIDENCE working in infant & early childhood mental health as:
 | 6.1067 | 8.24
Notes: Preliminary data also shows that overall staff rated having HIGHER CONFIDENCE after the last session/module in working in infant and early childhood mental health.

## Slide 18: Pulse Check: Key Accomplishments to Infrastructure for implementation of EBP in FFY 2023
Mentor Community of Practice
    Mentor coaching support
    Inter-rater reliability activity
Electronic coaching summary tool data roll-up
    In process of uploading and analyzing coaching log data
Mentor Position Filled – January 2024
Next Cohort Began- July 2024
Notes: Our key accomplishments for implementing evidence-based practices include:
Mentor Community of Practice – state and program mentors continue to meet with the focus of supporting mentors through activities such as open-mic for mentor coaching support and problem solving, coaching inter-rater reliability discussions to keep up on mentoring practices, and discuss and provide feedback on the coaching fidelity process, tools, and resources.
We are in process of uploading and analyzing coaching log data from demonstration site staff and mentors. The data roll-up feature is being piloted as a mechanism to gather and analyze fidelity data to determine, strengths, challenges, and trends to inform our coaching and mentoring process.
Last year a state position was established whose primary responsibility is comprised around mentoring. This position was filled in January 2024 and helped to finalize our coaching criteria and electronic summary tools for CCs, direct service providers, and new mentors. Training modules were also updated.
Training of the next cohort (Kona and North HI programs) was scheduled and began in July 2024.

## Slide 19
EKG Report: What does the data tell us?
Target 75% = Not Met
Slippage from 73% last year
Practicing Fidelity = 68%
Expanding Fidelity = 22%
Beginning Fidelity = 10%
Chart: Coaching Fidelity Status 6.30.24
| Beginning Fidelity | Expanding Fidelity | Practicing Fidelity
Coaching Fidelity Status 6.30.24 | 9.6 | 22.5 | 67.7
Coaching Fidelity Status 6.30.25 | 3 | 7 | 21
Notes: The coaching fidelity target of 75% was not met this year and had some slippage in comparison with June 2023 where we were at 73%.
Total providers and mentors during this data period was = 31 (with an additional 12 in process or new/not enough data to make a fidelity determination)
Reasons for this slippage include lost of staff due to turnover or staff retiring.
As new staff was hired, more staff were in process and then moved into beginning or expanding fidelity status.
Loss of mentors and mentors were being pulled to direct service and other responsibilities to cover vacancies which impacted their ability to consistently provide coaching and mentoring support.
Additional Notes:
December 2023 (total providers and mentors = 26 with 17 in process)
Practicing Fidelity = 88% (23)
Expanding Fidelity = 8% (2)
Beginning Fidelity = 4% (1)

## Slide 20
Pulse Hiccups: Challenges
Staff turnover/vacancies in Demo Sites and state level
New staff are unable to participate in IMH training
New managers unable to participate in RSC training
Coaching – time intensive, implementation
Retaining staff that have reached fidelity
Sustainability of Mentors
Notes: In the implementation phase we continue to be challenged to keep all of the pieces moving forward.
Ongoing staff turnover/vacancies results in multi-level challenges and impact the quality of implementation of the PSP approach and coaching, including:
  Need for trainings to constantly be scheduled and completed as new staff and managers come onboard
  New assignments of Mentors and scheduling of monthly coaching meetings for new staff is challenging
  Program teams need time to adjust to staff that resigned, and new staff coming in and learning process and procedures.
  When vacancies (short and long-term) occur, staff who remain need to take on things like larger case loads and additional responsibilities which impact their ability to implement practices with fidelity.
Coaching "fidelity process" is time intensive
  Reaching fidelity is a lengthy process for both the provider and mentor. This includes scheduling and completing monthly meetings with their mentor; writing up coaching logs/observation self-assessment after a visit; reviewing coaching logs.
  We are currently in discussions w/ other states re: their fidelity process and EIS is also reviewing the fidelity process to see what changes we can make to address this challenge.
Sustainability of Mentors: Mentoring continues to be done by staff who have other primary responsibilities.
  Includes: Program Managers, Direct service providers & care coordinators, Supervisors, Technical Support Staff.
  The time intensity of providing mentoring support increases exponentially when you mentor several providers and impacts their primary job duties.
  Our current mentors do not have adequate time to dedicate solely to mentoring.

## Slide 21: Maintaining a Steady Pulse – Next Steps
  Continued participation in the IECMH cross-state TA
  Continued TA to programs in implementation of the PSP approach to teaming & coaching
  Complete data roll-up of the electronic coaching summary as a mechanism for data collection and analysis
  Pilot the mentor capacity worksheet
  IMH & RSC Data Analysis
  Develop Infant Mental Health training modules
  Continue implementation of coaching fidelity with Cohort 1
  Identify SE competencies
  Extension of RSC small group support for Program Managers & Leadership
Notes: As we reflect on what was accomplished, challenges, and what will/may impact us in the future, next steps include:
Continued participation in the IECMH (Infant & Early Childhood Mental Health) cross state TA
Continued TA to support program implementation of the PSP approach to teaming and coaching
Complete data roll-up of the electronic coaching summary as a mechanism for data collection
We will be piloting the mentor capacity worksheet to determine drafted activities and time allotted are an accurate reflection of a mentor
IMH & RSC data analysis
Work with AIMHHI (Association for Infant Mental Health Hawaii) to develop Infant Mental Health modules based on the training that was completed
Continue implementation of coaching fidelity with Cohort 1 (Kona and North HI program manager and staff)
Identify SE competencies that incorporate IMH components into our EI system
Extension of RSC small group support for Program Managers and Leadership in 2025.

## Slide 22: Fiscal Staffing
  Short-term Outcomes:
  EI Programs will have sufficient staff to implement EBPs and supports to children and families
Notes: Jeff

## Slide 23
  Current Activities and Steps:
Activities | Steps
Identify and implement the teaming structure necessary to implement the PSP approach to teaming. | Determine geographic teams Determine staff allotment for each geographic team DONE
Identify and implement teaming structure necessary to implement the coaching model in natural learning environments. | Identify appropriate number of mentors needed for the coaching fidelity process. Identify staffing structure needed for mentors DONE
Develop a process for EI programs to access providers specializing in behavioral support. | Identify roles and responsibility of the BSS Identify qualifications for a BSS Develop a process to determine the need for BSS Develop a process to access BSS DONE
Identify and disseminate effective recruitment and retention strategies. | Explore national recommendations for recruitment and retention strategies Collaborate with the state initiative CSPD Recruitment and Retention Workgroup on effective strategies FLYER Done and will be distributed to programs
Fiscal Staffing
Notes: These are our current activities and steps that will help us reach those activities. (READ SLIDE LEFT TO RIGHT)

## Slide 24: Pulse Check: Staffing Key Accomplishments in FFY 2023
Geographic Teams Guidance- Implemented
Drafted Program Staffing Guidance-Completed
Mentor Capacity Worksheet-Completed (notes: EIS will pilot since mentor position has been filled)
Recruitment & Retention Strategy Options Flyer – Completed (to be distributed)
Steady workgroup participation
Notes: These are the key accomplishments of the Staffing Workgroup:
The purpose of the geographic team guidance is to provide EI programs guidance on how to establish assigned geographic service area boundaries when a program splits into 2 or more teams.
The mentor Capacity worksheet is to help determine the capacity of a full time mentor. This will help during the teaming rollout process by identifying how many mentors are needed to support each program.
The purpose of the Program Staffing guidance is to provide the programs with a breakdown of the staffing needs care coordinators and service providers based on the average enrollments.

## Slide 25
Pulse Hiccups: Challenges
On-going staff turnover/vacancies
Notes: These are some of the challenges the Staffing workgroup encountered:
Jeff
On-going staff turnover/vacancies: This is an ongoing issue. The workgroup continues to identify root causes for the staff turnover and vacancies and develop strategies as part of recruitment and retention. Although this list looks like a short list of issues staff turnover and vacancies are a true barrier to creating the documents we need to for our workgroup as well as a big hindrance for programs to be able to implement the coaching model.
Membership: Due to scheduling conflicts and other logistic issues the group didn’t have much traction in the beginning of 2022 but since has added consisting members who have contributed to the creation of the documents,

## Slide 26: Maintaining a Steady Pulse – Next Steps
Recruitment & Retention Flyer Distribution
Identify new goals for the Fiscal-Staffing workgroup
Notes: Jeff
Review slide
Geographic teams guidance, Mentor Capacity worksheet and Program Staffing Guidance will be presented to the SSIP leadership team as well as EIS for feedback. Changes will be made and we will get feedback from program managers and stakeholders. We weren't quite ready to share it today as it is still a rough draft.
The group will work on Identifying recruitment and retention strategies that work both nationally as well as locally and create deliverables to share with programs.

## Slide 27: Monitoring and Accountability
  Short-term Outcomes:
  EI providers and families will understand the COS process
  EI program managers will have the access and skills needed to use COS data for program improvement
Notes: Our short term goals remains …
How do we know that providers and families understand the COS process?
The COS process captures some very valuable information on how a child is functioning in the three outcome areas. How are programs using this data to create meaningful outcomes to improve the child’s functioning in areas of delay, as well as improve ratings in these areas?

## Slide 28: Monitoring and Accountability
  Current Activities to meet Outcomes:
  COS Fidelity observations.
  Support Program Managers in utilizing their Corrective Action Plan to identify root causes and aid in creating strategies for program improvement in child outcomes.
  COS questions added to the annual family survey.
  COS Knowledge Check (COS-KC).
Notes: The COS Fidelity observations are in the process of being finalized. Details for roll out are being addressed in the M&A workgroup.
The Corrective Action Plan has been modified to better enable Program Managers to use the CAP process as a means to addressing specific challenges facing their program. Support is provided by each programs respective QA.
Family understanding of the COS process continues to be measured through the family survey.
The COS Knowledge Check was completed by all staff in the last year, and will be added to the new hire orientation checklist.

## Slide 29
Current COS Fidelity Tool

## Slide 30: Annual Family Survey
Notes: These are the three questions added…(read)

## Slide 31: Family’s Understanding of the COS Process
Notes: This is our data from both this year and last year. Some things to note:
Kailua is no longer a demo site, so data was not entered into this table.
Overall, our results improved from last year, with just a very small dip in the statewide average.
We received about 248 more responses than last year.
The percentage for each question is based on total number of responses.
The overall score is based on the number of families who answered at least 2 out of the three questions, and scored a mean of 4 or above.
If a family only answers one of the three questions, their response will be counted for that questions, but not for the overall since they did not answer enough questions. Or if their average for the three questions falls below the “4” it is counted as did not agree.

## Slide 32
Family’s Understanding of the COS Process
Notes: In trying to measure a family’s understanding of the COS process, there are many different ways to analyze the data. This table looks at family’s responses by the length of time their child was receiving services and the age of the child at the time of the survey. Why I chose these are because programs have reported that families often do not understand child development when they first enter EI, and may be rating their child higher or lower than the team feels is accurate.
Children who have only received services for 6 months or less are closest to that initial IFSP and may have a better recollection of the process and their involvement in it. The percentages are very similar to the overall state percentages, although I cannot determine if the difference is statistically significant. It just seems that with that small of a difference, the overall takeaway is that families feel they do understand COS, they participated in the COS ratings, and they felt it was helpful .
Children who were under a year old at the time of the survey are also those that are closest to that initial IFSP, and although their number is low (only 85 families), all of their percentages are above the statewide percentages.
These are good jumping off points for really looking deeper as to why, if families are reporting a good understanding of the COS process, do we consistently not meet the target?. We need to dig deeper for root causes if we want to improve our data.

## Slide 33: Pulse Check: Key Accomplishments
Training completed for COS Observers
COS-KC added to the EI Orientation checklist to be completed by all new direct service providers.
Notes: COS observers have completed the training on determining fidelity.
With most current staff completing the COS-KC, it will be added to the new hire orientation checklist to ensure all providers complete,

## Slide 34
Pulse Hiccups: Challenges
COS Fidelity Process in Progress
Limited use of COS data for IFSP outcome development
Many Program Managers have not been able to use their COS data for program improvement
Notes: With staffing challenges across the board, we have not been able to schedule COS observations. As we push up on the holidays, it would seem better to begin the process January 2024.
Teams struggle to tie in all the pieces of the IFSP process…incorporating MDE results into completing the COS and subsequently using data for the creation of IFSP outcomes. A challenge that has been voiced is the challenge of creating meaningful outcomes around identified areas of need when parents are not concerned with that area (which is sometimes the case with social/emotional delays. Families are often focused on tangible skills, such as walking or talking, and may not recognize challenges in the social/emotional domain and do not feel it is necessary to address it.)
Program Managers still struggle on how to use their data for program improvement. QAs are available to support program managers in using the CAP process to identify and target areas that need improvement, but it is still a struggle with staffing issues and numerous competing priorities.

## Slide 35
EKG Report: What does the data tell us?
Program managers need additional supports around using COS data for program improvement.
Family’s initial results seem to indicate a good understanding and participation in the COS process.
Challenges continue around the completion of the COS fidelity process
Notes: All Program Managers statewide were trained in the process, however feedback received was that only one had actually tried out the process with staff, and the feedback was positive both from the PM and the staff.
Families continue to report that they have a good understanding of the COS process, participate in the process and feel it helped them develop outcomes on their child’s IFSP.
Based on family Survey data, we need to figure out why there is inconsistency between what families are reporting and what our Indicator 3 data states.

## Slide 36: Maintaining a Steady Pulse – Next Steps
Child Outcomes Summary Knowledge Check (COS-KC)
COS Fidelity Process
Using COS data for program improvement
Notes: As previously mentioned the COS-KC will be added to the New Hire orientation checklist as a mandatory part of the new hire process.
M&A workgroup will flesh out the details of the roll out for the fidelity observation
TA’s (which right now is Jeff and myself) will continue to support programs in looking at their COS data. As the Child Outcomes Coordinator, I am always available for additional support as requested.

## Slide 37: Feedback
Small Group Discussions
Professional Development & Technical Assistance
Fiscal- Staffing
Monitoring & Accountability
Notes: Each table will have an opportunity to provide 2 rounds of feedback to our SSIP workgroups. Facilitators will be joining each groups.

## Slide 38: Ongoing Partner Engagement
  Participate in workgroups to:
    Analyze data
    Develop Improvement Strategies
    Evaluate Progress
    Develop and Implement activities designed to improve outcomes for children
Email: sheri.umakoshi@doh.hawaii.gov
Notes: Thank you for sharing your ideas and suggestions. We are seeking Ongoing Partner Engagement through workgroups. We ask that you consider joining one of our workgroups.
Participating in a workgroup will include analyzing data, developing improvement strategies, evaluating progress, and developing and implementing activities to improve the outcomes for our children.
If you are interested in supporting us through a workgroup, please add your name, agency (if applicable), and email address to Sheri Umakoshi.

## Slide 39: THANK YOU!